## TestCase
| Product Name |  | Ajker Deal |  | TC Start Date | 17/9/2024 | TC Execution Start Date | 17/02/2024 |  |  |  | TEST CASE
| Module Name |  | Menubar,User Management |  | TC End Date | 22/9/2022 | TC Execution End Date | 20/02/2024 |  |  |  | PASS | 44
[5 empty] | Test Case Developed By | FARAH | Browser (tested) | 1 |  |  |  | FAIL | 10
| Developer Name (TL) |  | x |  | Test Case Reviewed By |  | Performance (tested) | No |  |  |  | Not Executed | 0
[12 empty] | Out of Scope | 0
[12 empty] | TOTAL | 54
#SL | Module | Type of Testing | Features | Section | Test Cases | test Data | Reporducing Steps | Exepected Result | Actual Result | Bug Screen Shot | Dev Comments | Final Status | Remarks
TC-001 | Menubar | UI Testing | Home Page |  | Check all the text box alignment ,ratio, colours ,logo | N/A | 1.go to url with broswer 2.observe the Home page,there are a menubar with 6 features such as Merchent Corner, Complain & Suggestion,Track order,Login,Bangla & English | all text boxes,font, ratio ,colour ,buttons, dropdown are perfect | UI should be perfect |  |  | Passed
TC-002 |  |  |  |  | Hovering option should change its color | N/A | 1.go to url with broswer 2.observe the Home page,there are a menubar with 6 features such as Merchent Corner, Complain & Suggestion,Track order,Login,Bangla & English | hovering on changes color when cursure touch the menu option | Found as per expected |  |  | Passed
TC-003 |  |  |  |  | Check translated mistake from Eng to Bang, spelling mistake or grammatical mistake | N/A | 1.go to url with broswer. 2.observe the Home page and point the menubar 3.Check the catagoris and its product item | page should not contain any mistake | page should not contain any grammatical mistake but there are few translations and spelling mistake | https://prnt.sc/MG-3D16IoX61 |  | Failed | 1.in men shopping section there was a product name is chinos when you translate to bangla langluage,it shows chino which is not appropiate word. 2. in women shopping section there was a jewellwey name is earing translation is not same in bangla language
TC-004 |  |  |  |  | Check the arrow sign are not going outside of the border. | N/A | 1.go to url with broswer. 2.observe the Home page 3.Check the catagoris and its product item | all arrow sign should be asign perfectly | found mistake in sign allignment | https://prnt.sc/NJXegd624dwJ |  | Failed
TC-005 | User Management | UI Testing |  | Register Page | Checking register form works properly | N/A | 1.go to url with broswer 2.observe the Home page, there are a menubar with 6 features such as Merchent Corner, Complain & Suggestion, Track order,Login,Bangla & English 3.click on login button ,its come with dropdown and found 4 option like login form ,registration,how to placeorder and refund policy. register option shown. 4.click on register button. | It should be works properly | found as expected |  |  | Passed
TC-006 |  |  |  |  | Checking register form's text and translation and alignment | N/A | 1.go to url with broswer 2.observe the Home page, there are a menubar with 6 features such as Merchent Corner, Complain & Suggestion, Track order,Login,Bangla & English 3.click on login button ,its come with dropdown and found 4 option like login form ,registration,how to placeorder and refund policy. register option shown. 4.click on register button. | It should show the proper text, alignment and translation | there are found a mistake that is when user choose the English language but show the interface of registration form in bangla | https://prnt.sc/g3Tw-1mLR_n8 |  | Failed
TC-007 |  | Functional | Registration | Name | checking the registration from without input any data | N/A | 1.go to url with broswer 2.observe the Home page, there are a menubar with 6 features such as Merchent Corner, Complain & Suggestion, Track order,Login,Bangla & English 3.click on login button ,its come with dropdown and found 4 option like login form ,registration,how to placeorder and refund policy. register option shown. 4.click on register button. | It should not be register and show a message in every field to fill up this field | Not registered but showing a warning message. |  |  | Passed
TC-008 |  | Positive |  |  | Checking the Name field without any data | N/A | 1.go to url with broswer. 2.then going to login option 3.register button click . 4. Do not enter any value in the Name field. 5.Click on the Register button. | should not submited without Name | found as expected |  |  | Passed
TC-009 |  | Negetive |  |  | Checking the Name field accept the number or not | 1234567 | 1.go to url with broswer. 2.then going to login option 3.register button click . 4. Enter only number on name field 5.Click on the Register button. | should not submited with number | found mistake ,registered name with only number | https://prnt.sc/meAvXvlSZoJj |  | Failed
TC-010 |  | Negetive |  |  | Checking the name field accept number text and symbol combinition | Sham12@*# | 1.go to url with broswer. 2.then going to login option 3.register button click . 4. Entry a combinitin value in name field 5.Click on the Register button. | should not submited with number,text and symbolic combinition | found mistake ,registered name with various combinition | https://prnt.sc/DZuctWwA06si |  | Failed
TC-011 |  | Negetive |  |  | Name field with preceding space inputs | Farah | 1.go to url with broswer. 2.then going to login option 3.register button click . 4. Entry name with space 5.Click on the Register button. | should not take preceding space | as per expect |  |  | Passed
TC-012 |  | Functional |  |  | Check user should Register by filling all the required fields with vaild infromation | name-Farah Naj email-najprof.22@gmail.com phn number- 01950084003 password-sham1234 confirm password- sham1234 | 1.go to url with broswer. 2.then going to login option 3.register button click . 4. fill the fields with valid info. 5.Click on the Register button. | should be registered | user registration works proparly |  |  | Passed
TC-013 |  | functional |  | Mobile Number | Check the mobile number accept less then 11 digit(BD) | 195008400 | 1.go to url with broswer. 2.then going to login option 3.register button click . 4. fill the Mobile Number field with 10 digit number 5.Click on the Register button. | should not submitted and showing a warning messege | found as per expected |  |  | Passed
TC-014 |  | functional |  |  | Check the mobile number accept more then 11 digit(BD) | 19500840031 | 1.go to url with broswer. 2.then going to login option 3.register button click . 4. fill the Mobile Number field with 10 digit number 5.Click on the Register button. | should not submitted and showing a warning messege | found as per expected |  |  | Passed
TC-015 |  | Positive |  | Email | Email field with empty mail address | N/A | 1.go to url with broswer. 2.then going to login option 3.register button click . 4. .Don't enter any email 5.Click on the Register button. | warning message should be showed. | found as per expected |  |  | Passed
TC-016 |  | Negetive |  |  | Email field with invalid mail address | naj.11@gma.com | 1.go to url with broswer. 2.then going to login option 3.register button click . 4. fill the fields with invalid info. 5.Click on the Register button. | Should show a warning message | found as not expected | https://prnt.sc/dKjsDomCbD6u |  | Failed
TC-017 |  | Negetive |  |  | Email field with numbers | 12345678987654321 | 1.go to url with broswer. 2.then going to login option 3.register button click . 4. fill the fields with number. 5.Click on the Register button. | Should show a warning message | found as expected |  |  | Passed
TC-018 |  | Positive |  |  | Email filed validation checking | najprof.22@gmail.com | 1.go to url with broswer. 2.then going to login option 3.register button click . 4. fill the fields with valid info. 5.Click on the Register button. | should take vaild gmail address . | as per expected |  |  | Passed
TC-019 |  | Positive |  |  | checking Email field with already existed mail id | najprof.22@gmail.com | 1.go to url with broswer. 2.then going to login option 3.register button click . 4. fill the fields with existing email. 5.Click on the Register button. | an error message should appear under email field | as per expected |  |  | Passed
TC-020 |  | negative |  | Password | Password field empty | N/A | 1.go to url with broswer. 2.then going to login option 3.register button click . 4. do not entry any value 5.Click on the Register button. | An error message should appear under password field | as expected |  |  | Passed
TC-021 |  | positive |  |  | Password field with alphabets | shamhappyone | 1.go to url with broswer. 2.then going to login option 3.register button click . 4. fill the fields with alphabet. 5.Click on the Register button. | should accept | as expected |  |  | Passed
TC-022 |  | positive |  |  | Password field with special characters | #@!&(* | 1.go to url with broswer. 2.then going to login option 3.register button click . 4. fill the fields with number. 5.Click on the Register button. | should accept | as expected |  |  | Passed
TC-023 |  | positive |  |  | Password field with numbers | 12345678 | 1.go to url with broswer. 2.then login 3.click on register button click . | should accept | as expected |  |  | Passed
TC-024 |  | positive |  |  | Password field with lower and upper case alphabets | SHaaM | 1.go to url with broswer. 2.then going to login option 3.register button click . 4. fill the fields with lower case & upper case. 5.Click on the Register button. | should accept | as expected |  |  | Passed
TC-025 |  | positive |  |  | Password field with space inputs with characters | 123 456 | 1.go to url with broswer. 2.then going to login option 3.register button click . 4. fill the fields with space. 5.Click on the Register button. | should accept | as expected |  |  | Passed
TC-026 |  | boundary |  |  | password field lower and upper boundray (8 to infinity) | 1234567 | 1.go to url with broswer. 2.then going to login option 3.register button click . 4. fill the fields with lower and upper boundary. 5.Click on the Register button. | should accept | there are no restraction for follwing lower and upper boundary rules | https://prnt.sc/8jnlLMBXb6K9 |  | Failed
TC-027 |  | functional |  |  | password should be masked |  | 1.go to url with broswer. 2.then going to login option 3.register button click . 4. fill the fields with mask. 5.Click on the Register button. | expected not to show the password when user are typing | found as expected |  |  | Passed
TC-028 |  | functional |  |  | Clicking pick icon on password field | 12345678 | 1.go to url with broswer. 2.then going to login option 3.register button click . 4. click the icon which help to show the hidden password. 5.Click on the Register button. | Written password should be visible | not found as expected | https://prnt.sc/78akVeGFiDiX |  | Failed
TC-029 |  | positive |  |  | confirmed password validation | 12345678 | 1.go to url with broswer. 2.then going to login option 3.register button click . 4. fill the fields with valid info 5.Click on the Register button.. | should accept | found as expected |  |  | Passed
TC-030 |  | functional |  |  | Checking otp validation |  | 1.go to url with broswer. 2.then going to login option 3.register button click . 4.Click on the Register button. 5. check the email or mobile messege otp for varifying account | should send message on phone number or email address | no otp messege send to mobile number or email | https://prnt.sc/u-3a60O2CNFY |  | Failed
TC-031 |  | postive |  |  | hovering the mouse should highlight the button |  | 1.go to url with broswer. 2.then going to login option 3.register button click . 4.Click on the Register button. 5. hovering the cursur on register button | highlights the register button | as expected |  |  | Passed
TC-032 |  | functional |  |  | siging up with gmail | N/A | 1.go to url with broswer. 2.then going to login option 3.register button click . 4.Click on the Register button. 5. chooce a varified gmail accound from list | should be logged in | as expected |  |  | Passed
TC-033 |  | Non -functional | Log In |  | Verifying whether Sign In page appears | N/A | 1.go to url with broswer 2.observe the Home page, there are a menubar with 6 features such as Merchent Corner, Complain & Suggestion, Track order,Login,Bangla & English 3.click on login option ,its come with dropdown and found 4 option like login form ,registration,how to placeorder and refund policy. register option shown. 4.check login form | A Sign In UI should appear | as expected |  |  | Passed
TC-034 |  |  |  |  | Grammatical or spelling mistake on Sign In page | N/A | 1.go to url with broswer 2.observe the Home page, there are a menubar with 6 features such as Merchent Corner, Complain & Suggestion, Track order,Login,Bangla & English 3.click on login option ,its come with dropdown and found 4 option like login form ,registration,how to placeorder and refund policy. register option shown. 4.check login form | should not found any grammatical or spelling problem | as expected |  |  | Passed
TC-035 |  |  |  |  | checking all text boxes, size, font, aligment for sign in page | N/A | 1.go to url with broswer 2.observe the Home page, there are a menubar with 6 features such as Merchent Corner, Complain & Suggestion, Track order,Login,Bangla & English 3.click on login option ,its come with dropdown and found 4 option like login form ,registration,how to placeorder and refund policy. register option shown. 4.check login form | all text boxes are size ,font colour are ok | as expected |  |  | Passed
TC-036 |  | positive | Log IN |  | checking with valid email id and password | najprof.22@gmail.com sham1234 | 1.go to url with browser 2. Click on "Sign In" button. 3. A new page will appear having Sign In button. | user should logged in | as expected |  |  | Passed
TC-037 |  | negative |  |  | checking with invalid email id and valid password | najprof@gmail.com sham1234 | 1.go to url with browser 2. Click on "log In" button. 3. A new page will appear having Sign In button. | an error message showed | as expected |  |  | Passed
TC-038 |  | negative |  |  | checking with valid email id and invaild password | najprof.22@gmail.com naj123456 | 1.go to url with browser 2. Click on "log In" button. 3. A new page will appear having Sign In button. | an error message should be showed | as expected |  |  | Passed
TC-039 |  | negative |  |  | checking with invalid email id and invaild password | najprof@gmail.com naj123456 | 1.go to url with browser 2. Click on "log In" button. 3. A new page will appear having Sign In button. | an error message should be showed | as expected |  |  | Passed
TC-040 |  | functional |  |  | checking Remember Me option clickable or not | N/A | 1.go to url with browser 2. Click on "log In" button. 3. A new page will appear having log In button. | should be clickable or not | there has no "Remember Me" option | https://prnt.sc/W1ms8CAu7_Rt |  | Failed
TC-041 |  | functional |  |  | Checking password field is masked |  | 1.go to url with browser 2. Click on "log In" button. 3. A new page will appear having Sign In button. | Written password should be masked | as expected |  |  | Passed
TC-042 |  | functional |  |  | hovering the mouse should highlight the button |  | 1.go to url with browser 2. Click on "log In" button. 3. A new page will appear having Sign In button. | highlights the log in button | as expected |  |  | Passed
TC-043 |  | functional |  |  | checking "forgot password" button | N/A | 1.go to url with browser 2. Click the login option and found login form and forgot password option 3.Click on "Forget Password" button. 3. A new page will appear | should lead to a recovery email address or mobile number | as expected |  |  | Passed
TC-044 |  | positive |  |  | checking with valid email,mobile number for reset password | 1950084003 | 1.go to url with browser 2. Click the login option and found login form and forgot password option 3.Click on "Forget Password" button. 3. A new page will appear | should send a otp in mobile address | as expected |  |  | Passed
TC-045 |  | negative |  |  | checking with invalid mobile number for reset password | 195008400 | 1.go to url with browser 2. Click on "log In" button. 3. A new page will appear having Sign In button. 4.click forgot password button 5.shows reset password page. | should show an warning message | as expected |  |  | Passed
TC-046 |  | functional |  |  | copying password paste on text box | 12345678 | 1.go to url with browser 2. Click on "log In" button. 3. A new page will appear having Sign In button. 4.click forgot password button 5.shows reset password page. | should be accpectable | as expected |  |  | Passed
TC-047 |  | functional |  |  | checking hyperlink takes correct tab | https://ajkerdeal.com/customers/registersingleorder.aspx | 1.go to url with browser 2. Click on "Log In" button. 3. A new page will appear having Sign In button | should take us to proper place | as expected |  |  | Passed
TC-048 |  | functional |  |  | checking hyperlink wrong text | https://ajkerdeal.com/customers/registersingleorder | 1.go to url with browser 2. Click on "Sign In" button. 3. A new page will appear having Sign In button | showing the error messege | as expected |  |  | Passed
TC-049 |  | functional |  |  | after clicking or selecting an option,dropdown should be highlighted. | N/A | 1.go to url with browser 2. Click on "Sign In" button. 3. A new page will appear having Sign In button | should be highlighted | as expected |  |  | Passed
TC-050 |  | Non-Functional |  |  | checking mouse cursor change according to ui element | N/A | 1.go to url with browser 2. Click on "Sign In" button. 3. A new page will appear having Sign In button | should be change according to UI element | as expected |  |  | Passed
TC-051 |  | Usability |  |  | application works on ios/android mobile | N/A | 1.go to url with browser 2. Click on "Sign In" button. 3. A new page will appear having Sign In button | should be works properly | as expected |  |  | Passed
TC-052 |  | Browser Compatibility Testing |  |  | application works on browsers like google chrome, mozilla firefox. | N/A | 1.go to url with browser 2. Click on "Sign In" button. 3. A new page will appear having Sign In button | should be works properly | as expected |  |  | Passed
TC-053 |  | Usability |  |  | application works on ios/android mobile | N/A | 1.go to url with browser 2. Click on "Sign In" button. 3. A new page will appear having Sign In button | should be works properly | as expected |  |  | Passed
TC-054 |  | Browser Compatibility Testing |  |  | application works on browsers like google chrome, mozilla firefox. | N/A | 1.go to url with browser 2. Click on "Sign In" button. 3. A new page will appear having Sign In button | should be works properly | as expected |  |  | Passed

## Report
Test Case Report
Project Name - | Fabrilife
Module Name - | Home Page,Registration,sign in |  |  |  |  | Total No. | Status | Result :
Test Case Version | - |  |  |  |  | 44 | PASS
Written By | Farah |  |  |  |  | 10 | FAIL
Executed By | Farah |  |  |  |  | 0 | Not Executed | New Features | Testing Scope | Testing Environment :
Reviewed By | - |  |  |  |  | 0 | Out of Scope |  |  | Test Environment | Google Chrome Browser
TEST EXECUTION REPORT
Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total TC
| 44 | 10 | 0 | 0 | 54
Grand Total | 44 | 10 | 0 | 0 | 54
LIMITATIONS
Documents |  |  |  | Received | Useful
PRD |  |  |  | No | No
USER STORY |  |  |  | No | No
| Testing Type in Scope | Description
Yes/ No. Justification (If No): | Functional Testing | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not.
Yes/ No. Justification (If No): | Integration Testing | Testing of all integrated modules to verify the combined functionality after integration is termed as Integration Testing.
Yes/ No. Justification (If No): | Negative Testing | Testing having the mindset of “attitude to break” using incorrect data and invalid inputs.
Yes/ No. Justification (If No): | Usability Testing | Test application from user friendliness perspective.
Yes/ No. Justification (If No): | Browser Compatibility Testing | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether web application runs on all versions of all browsers or not.
Yes/ No. Justification (If No): | Boundary Value Testing | There is an upper and lower boundary for each range and testing is performed on these boundary values.
Yes/ No. Justification (If No): | Risk Based Testing Or Regression Testing | Risk-Based Testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high. Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing.

## Bug Report
Bug Report
TC-012
Issue: do not reset the otp timer if user tries to register again changing the information on register option
Reproducing Steps:
1.go to url with broswer.
2.then login option comes with dropdown where 3 options come which is login, register, ordertrack.
3.register button click .
4. fill the fields with valid info.
5.Click on the Register button.
Env: Production
Module: Sign Up
Severity: P1
Bug Screenshot: | https://prnt.sc/lPHYR0joBOvU --> https://prnt.sc/dLeYVpr02x9j
Responsible QA: Anushka, Saddam, Reem

## Test Metrics
Testing Metrics
Area | Formula | Data | Percentage %
Excuted Test Cases | (Number of Excuted Test cases/Total number of test case written) X 100 | (70/70)X 100 | 100%
Not Excuted Test Cases | (Number of not Excuted Test cases/Total number of tests executed) X 100 | (0/70)X 100 | 0%
Passed Test Cases | (Number of Passed Test cases/Total number of executed test cases) X 100 | (60/70)X 100 | 85.71%
Failed Test Cases | (Number of Failed Test cases/Total number of executed test case) X 100 | (10/70)X 100 | 14.29%
Blocked test cases | (Number of Tase Case Blocked/ Total number of executed test case) X 100 | (0/70)X 100 | 0%
Defect density | (Number of defects found/Size(number of requrements)
Defect Leakege | (Number of defects found in UAT/number of defect found in test) X 100 | (0/0)X 100 | 0%
Defect Rejection | (Number of defect rejected/number of total defect found rasied) X 100 | (0/0)X 100 | 0%
DRE(Defect removal Efficiency) | (A/A+B) 100 Where, A means Defect ldentified/Fixed Defects, B means defect identified by customers/issued defects | 100 | 100%
Defect Age | Fixed date- Reported date | N/A | N/A